## Project Dashboard
CAMINNA CRM
Project Control Dashboard
Reporting Date | 2026-10-23
Next Milestone |  | Milestones Completed |  | Critical Risks
MVP Backlog |  | 33.33% |  | 1
Project Timeline
Current Phase | Phase 2 | Next Phase | Phase 3
Current Phase Name | Product Discovery and Backlog | Next Phase Name | CRM Configuration
Objective | Translate business needs into an actinoable backlog | Objective | Build the CRM Solution
Key Activities | User Stories MVP definition | Key Activities | Salesforce Configuration
Deliverables | Jira Backlog MVP | Deliverables | Salesforce CRM prototype
Duration | 2 days | Duration | 3 days
Upcomping Tasks
| Task | Description
Current Task | User Stories | Write user stories and acceptance criteria
Next Task | MVP Priorization | Priorize the backlog and define the MVP scope
Nexts Tasks | Data Model Setup | Configure Salesforce objects (accounts, opportunities…)

## Timeline
Phase | Phase Name | Objective | Key Activities | Deliverables | Duration | Completed
Phase 1 | Project Initiation and Planning | Define the project scope | Stakeholder identification Project Charter Requirements | Project Charter Project Planning | 2 days | TRUE
Phase 2 | Product Discovery and Backlog | Translate business needs into an actinoable backlog | User Stories MVP definition | Jira Backlog MVP | 2 days | FALSE
Phase 3 | CRM Configuration | Build the CRM Solution | Salesforce Configuration | Salesforce CRM prototype | 3 days | FALSE
Phase 4 | Testing and Validation | Validate the new requirements | Test Cases UAT | Test Plans UAT Results | 2 day | FALSE
Phase 5 | Project Closure | Evaluate final results and documentation of the project | KPI New discoveries Final documentation | KPI results Final Documentation | 1 day | FALSE
Milestones | Description | Target Date | Completed
Project Charter Approved | Project Scope and objectives approved | Day 1 | TRUE | Percentage Completed | 33.33%
Requirements Completed | Requierements and stakeholders need defined | Day 2 | TRUE
MVP Backlog | User stories done and prioritised | Day 4 | FALSE
CRM Prototype | Salesforce CRM configure | Day 7 | FALSE
UAT Completed | CRM tested | Day 9 | FALSE
Project Closure | KPIs and final documentation | Day 10 | FALSE

## Work Planing
Code | Task | Description | Owner | Status
1.0 | Project Management | Governance, Scope and Risk Management | PM | TRUE
1.1 | Project Charter | Define and approve he project scope, objectives and main stakeholders | PM | TRUE
1.2 | Project Schedule | Define the project schedule, phases and milestones | PM | TRUE
1.3 | Risk Management | Identify risks, assess their impacts and define mitigation plans | PM | TRUE
2.0 | Product Management | Requirements and Backlog Definition | PO | FALSE
2.1 | Product Discovery | Identify user profiles and business needs | PO | TRUE
2.2 | User Stories | Write user stories and acceptance criteria | PO | FALSE
2.3 | MVP Priorization | Priorize the backlog and define the MVP scope | PO | FALSE
3.0 | CRM Implementation | Salesforce Prototype Build | Salesforce Consultant | FALSE
3.1 | Data Model Setup | Configure Salesforce objects (accounts, opportunities…) | Salesforce Consultant | FALSE
3.2 | Pipeline Stages | Configure sales pipelines stages based on business requirements | Salesforce Consultant + PO | FALSE
3.3 | Sample Data Load | Load 15-20 fictional records to support CRM testing | Salesforce Consultant | FALSE
4.0 | Quality Assurance | Testing and Validation | PO + Business Stakeholder | FALSE
4.1 | User Acceptance Testing Execution | Prepare and execute UAT to validate the CRM solution | PO + Sales Lead | FALSE
4.2 | KPI Framework | Define metrics to monitor performance | PM + PO | FALSE

## Risk Register
Risk ID | Category | Description | Probability | Impact | Owner | Mitigation Plan | Risk Score | Priority
R01 | Adoption | Sales representatives may continue using Excel instead of the new Salesforce solution beacuse is what they are used to | High | High | PO + Sales Lead | Listen their user experience and provide the correct onboarding to this new platform | 9 | Critical
R02 | Data Quality | Incomplete or duplciarte records from existing spreedsheets may reduce the accuracy of he solution | Medium | High | Salesforce Consultant | Define validation rules and mandatory fields and review the data before testing it | 6 | High
R03 | Scope | Additional automation may expand the initial MVP scope | High | Low | PM + PO | Prioritise requirements, assses change requesta and defer no-essential features | 3 | Medium
R04 | Technical | Limitation of the Salesforce Edition may prevent of the ideal features and pipelines to be implemented | Medium | Medium | Salesforce Consultant | Verify platform capabilities and permissions before starting the implementation | 4 | Medium

## Auxiliar
% Progress
Milestone Status | Count
Completed | 2
Pending | 4
Total | 6
Risk Priority
Priority | Count
Critical | 1
High | 1
Medium | 2
Low | 0
Gannt
Phase Nº | Phase Name | Duration | Start Day | Completed | Done | In Progress | Pending
Phase 1 | Project Initiation and Planning | 2 | 0 | TRUE | 2 | 0 | 0
Phase 2 | Product Discovery and Backlog | 2 | 2 | FALSE | 0 | 2 | 0
Phase 3 | CRM Configuration | 3 | 4 | FALSE | 0 | 0 | 3
Phase 4 | Testing and Validation | 2 | 7 | FALSE | 0 | 0 | 2
Phase 5 | Project Closure | 1 | 9 | FALSE | 0 | 0 | 1
Tasks Completion
Tasks Metrics | Value
Completed Tasks | 4
Pending Tasks | 7
Total Tasks | 11
Progress | 36.36%